## Instructions
Activities During the Planning Meet:
| Estimated Task Priority: | Each team member select a value between 0 (most unimportant) to 10 (most important) from the drop down list based on his/her own understanding about the task.
| Estimated Task Difficulty: | Each team member select a value between 0 (extremely easy) to 10 (extremely difficult) from the drop down list based on his/her own understanding about the task.
| Estimated Task Time Required: | Each team member select a value between 1 to 14 days from the drop down list based on his/her own understanding about the task.
| Confidence about the Task: | Each team member select a value between 0 (not confident at all) to 10 (extremely confident) from the drop down list based on his/her own understanding about the task and his/her own capabilities.
| Assignee's Mood: | Excited | Happy | Neutral | Sad | Depressed
| Task Assignee: | Team members should discuss among themselves to distribute the tasks. If there are tasks which remain unassigned after the discussion, team lead will decide to whom the remaining task(s) should be delegated.
Activities During the Subsequent Planning Meeting
Review for each task: if it has been completed (Yes/No), rate the quality of the result (0: Extremely Bad -10: Excellent)

## SRS Meeting
Task No. | Task Description | Team Member Name: | Team Leader | Deputy Leader | Member 1 | Member 2 | Member 3 | Member 4 | Average Task Priority | Average Task Difficulty | Average Task Deadline (days) | Task Assignee | Task Helpers | Task Allocation Method | Has the task been completed successfully? | Actual Days used to Complete the Task | Assignee's Mood after Completing this Task | Average Task Quality Rating
|  |  | Tang Kai Wen, Alvin | Yong Wen Shiuan | Heng Chor Chen, Sabrina | Bankata Mishra, Spriha | Gupta, Suhana | Heng Fuwei, Esmond
Team member's mood during the this week's meeting: |  |  | Excited | Neutral | Happy | Happy | Excited | Excited
1 | System Requirement Specification (Problem Statement) | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 1 | 1.1667 | Tang Kai Wen, Alvin |  | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 10 | 10 | 10 | 10 | 10
| Estimated Task Difficulty（0-10） |  | 1 | 1 | 1 | 1 | 1 | 1
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
2 | System Requirement Specification (Overview) | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 1.3333 | 1 | Tang Kai Wen, Alvin |  | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 9 | 9 | 9 | 9 | 8
| Estimated Task Difficulty（0-10） |  | 2 | 1 | 1 | 1 | 1 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 9 | 10 | 10 | 10 | 10 | 10
3 | System Requirement Specification (Investigation & Analysis Methodology) | Task Quality Evaluation (After Task Completed) | 10 | 7 | 10 | 10 | 10 | 10 | 8.5 | 4.1667 | 1.5 | Heng Fuwei, Esmond |  | Through Discussion | Yes | 2 | Happy | 9.5
| Estimated Task Priority（0-10） |  | 8 | 9 | 9 | 9 | 9 | 7
| Estimated Task Difficulty（0-10） |  | 2 | 5 | 5 | 5 | 5 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 1 | 1 | 1 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 8 | 4 | 4 | 4 | 4 | 9
4 | System Requirement Specification (Constraints) | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 8.5 | 6.1667 | 1.5 | Bankata Mishra, Spriha |  | Through Discussion | Yes | 2 | Happy | 10
| Estimated Task Priority（0-10） |  | 9 | 9 | 9 | 9 | 9 | 6
| Estimated Task Difficulty（0-10） |  | 5 | 7 | 7 | 7 | 7 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 2 | 1 | 1 | 1 | 1 | 3
| Team Member's Confidence about the Task (0-10) |  | 7 | 5 | 5 | 5 | 5 | 8
5 | System Requirement Specification (Functional Requirements) | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 8.5 | 2.3333 | 1.3333 | Yong Wen Shiuan |  | Through Discussion | Yes | 1 | Neutral | 10
| Estimated Task Priority（0-10） |  | 7 | 8 | 9 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 4 | 2 | 2 | 2 | 2 | 2
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 8 | 10 | 10 | 9 | 9 | 10
6 | System Requirement Specification (Input Requirements) | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 8.8333 | 2.5 | 1.5 | Heng Chor Chen, Sabrina |  | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 8 | 9 | 9 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 3 | 2 | 2 | 2 | 2 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 3 | 1 | 1 | 1 | 1 | 2
| Team Member's Confidence about the Task (0-10) |  | 8 | 8 | 10 | 8 | 8 | 8
7 | System Requirement Specification (Process Requirements) | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 9.1667 | 4.1667 | 1 | Yong Wen Shiuan |  | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 9 | 9 | 9 | 9 | 9
| Estimated Task Difficulty（0-10） |  | 1 | 6 | 5 | 5 | 5 | 3
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 10
8 | System Requirement Specification (Hardware Requirements) | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 8.5 | 2.6667 | 1 | Tang Kai Wen, Alvin |  | Through Discussion | Yes | 1 | Excited | 10
| Estimated Task Priority（0-10） |  | 10 | 8 | 8 | 8 | 8 | 9
| Estimated Task Difficulty（0-10） |  | 1 | 5 | 2 | 2 | 2 | 4
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 1
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 9
9 | System Requirement Specification (Software Requirements) | Task Quality Evaluation (After Task Completed) | 10 | 10 | 10 | 10 | 10 | 10 | 8.6667 | 2.8333 | 1.3333 | Yong Wen Shiuan |  | Through Discussion | Yes | 1 | Happy | 10
| Estimated Task Priority（0-10） |  | 10 | 5 | 9 | 9 | 9 | 10
| Estimated Task Difficulty（0-10） |  | 1 | 2 | 2 | 3 | 2 | 7
| Estimated Time Required for the Task（1-14 Days） |  | 1 | 1 | 1 | 1 | 1 | 3
| Team Member's Confidence about the Task (0-10) |  | 10 | 10 | 10 | 10 | 10 | 8